March 28, 2026

Construction Planning and Management _ Multiple Choice Questions

- Which statement about dummy activities in Activity-on-Arrow (AOA) networks is correct?

- They consume time but not resources

- They consume resources but not time

- They consume neither time nor resources

- They are used only in PERT calculations

- A country invests heavily in infrastructure such as roads, dams, and housing. Over time, employment increases, industrial output grows, and tax revenue improves. Which major role of the construction industry is best illustrated in this case?

- Environmental sustainability

- Income redistribution and economic stimulation

- Reduction of foreign dependency

- Minimization of labor demand

- During a building project, the contractor failed to conduct a proper site investigation before bidding. Later, unexpected soil conditions increased project cost and caused delays. Which responsibility did the contractor FAIL to fulfill?

- Failure to assess contractual risks associated with site conditions

- Delay in submission of variation claims to the consultant

- Inadequate supervision of subcontractors during execution phase

- Non-compliance with technical specifications during construction

- A project manager focuses on achieving project goals while minimizing waste of resources. Which statement correctly differentiates efficiency and effectiveness?

- Efficiency refers to achieving goals, while effectiveness refers to minimizing costs

- Effectiveness means doing things right, while efficiency means doing the right things

- Effectiveness refers to achieving goals, while efficiency refers to using resources optimally to achieve those goals

- Both efficiency and effectiveness refer to the same concept in project management

- Organizing as a management function mainly involves:

- Comparing actual performance with standards

- Assigning tasks, allocating resources, and establishing authority relationships

- Inspiring employees through leadership style

- Predicting future market conditions only

- Which scheduling method is best fit for projects with uncertain activity durations?

- Gantt Chart

- CPM

- Flowchart

- PERT

- In a large-scale construction project, a manager is required to integrate human, financial, and material resources efficiently while ensuring that project objectives are achieved within time and cost constraints. Which of the following best describes this process?

- A set of isolated activities focused only on financial planning and budgeting without coordination of other resources

- A structured process involving planning, organizing, staffing, directing, and controlling organizational resources to achieve defined objectives effectively and efficiently

- A temporary effort focused only on execution of construction works without involving planning and monitoring phases

- A process limited to supervising workers and ensuring quality of materials used in construction

- Which of the following best describes a milestone in project scheduling?

- A significant event with zero duration used to monitor project progress

- An activity requiring significant resources and time

- A task with flexible duration

- A critical path activity

- In CPM, the critical path is the sequence of activities that:

- Determines the shortest possible project duration

- Has the lowest cost

- Has the most workers assigned

- Can be delayed without affecting the project

- A government-funded road project in Ethiopia was planned to be completed in 24 months. However, due to poor coordination among stakeholders, shortage of skilled labor, delayed payments, and weak contract administration, the project extended to 40 months with a cost overrun of 35%. The consultant blames the contractor for poor planning, while the contractor claims that design changes and delayed approvals caused the problem. Which of the following is the MOST appropriate root cause of failure?

- Poor weather conditions affecting construction

- Weak institutional capacity and poor project management practices

- High cost of imported materials only

- Excessive government regulations

- A bid bond is primarily intended to protect the project owner against the risk that the bidder will:

- Fail to insure the workers

- Refuse to enter into the contract after being awarded the bid

- Delay material delivery during construction

- Submit interim payment certificates late

- Which level of management is mainly concerned with policy formulation, long-term planning, and overall organizational success?

- Supervisory management

- Middle management

- Top-level management

- Operational management

- Which scheduling technique is most suitable for handling uncertain activity durations?

- CPM                    B Gantt Chart             C. PERT             D. Line of Balance

- Which statement best describes a project?

- A routine activity performed continuously in an organization

- A permanent process with unlimited time

- A financial record of organizational activities

- A temporary endeavor undertaken to create a unique product, service, or result

- Which dependency means an activity cannot start until another activity is finished?

- Finish-to-Start

- Start-to-Start

- Finish-to-Finish

- Start-to-Finish

- Which organizational structure allows employees to report to more than one manager?

- Functional structure

- Divisional structure

- Matrix structure

- Line structure

- An activity has ES = 4, EF = 10, LS = 7, and LF = 13. What is its total float?

- 6

- 4

- 2

- 3

- While developing a network diagram for a construction project, the planner encounters a situation where two activities share a dependency relationship, but no actual work or time is required to represent this dependency. To correctly represent the logical relationship without affecting duration or resource allocation, a special type of activity is introduced. What is the purpose of this type of activity?

- To represent actual construction, work-consuming time and resources

- To increase the total duration of the project

- To illustrate logical relationships without consuming time or resources

- To identify critical activities in the project

- In a backward pass calculation, the latest finish time of an activity is primarily determined by:

- The earliest start of predecessor activities

- The latest start of successor activities

- The activity duration only

- The project budget

- Which of the following is the most likely disadvantage of too much centralization in an organization?

- Faster decision-making at lower levels

- Greater initiative among subordinates

- Delay in decisions and reduced flexibility

- Improved employee empowerment

- Which construction bond guarantees that the contractor will execute the work in accordance with the terms of the contract?

- Performance bond

- Bid bond

- Maintenance bond

- Payment bond

- Which managerial skill is most critical for first-line managers in construction projects?

- Conceptual skill

- Technical skill

- Strategic planning skill

- Financial forecasting skill

- A contractor is facing pressure to complete a project earlier than the original deadline due to contractual obligations. The project manager decides to reduce the duration of critical activities by allocating additional resources, which increases direct costs but reduces overall project time. What is the primary objective of this technique?

- To reduce project cost only

- To eliminate non-critical activities

- To increase project complexity

- To reduce project duration at minimum additional cost

- A contractor begins a construction project without properly planning the site layout. As a result, materials are stored in inefficient locations, equipment movement becomes difficult, and safety risks increase. This leads to delays and higher project costs. What is the most likely consequence of poor site layout planning?

- Improved efficiency and productivity

- Reduced project cost and time

- Better coordination among workers

- Operational inefficiencies and increased project cost

Answers

- C

- B

- C

- C

- B

- D

- B

- A

- A

- B

- B

- C

- C

- D

- A

- C

- D

- C

- B

- C

- A

- B

- D

- D